## Milestones
DHSE v2.0 — 18-Month Delivery Roadmap
Generated by Z.ai Engineering · Internal Architecture Brief
Quarter | Month Range | Theme | Track | Primary Deliverable | Exit Criterion | Owner | Status
Q1 | M1-M3 | Foundation | Foundation | MVP: single-style extraction + Bézier rendering + IndexedDB vault | CER < 15% on internal dataset | Eng | Planned
Q1 | M1-M3 | Foundation | Foundation | IndexedDB vault + AES-GCM encryption | Zero network calls verified | Security | Planned
Q1 | M2-M3 | Foundation | Foundation | Canvas rendering + power-law modulator prototype | 60fps on M1 MacBook Air | Eng | Planned
Q2 | M4-M6 | Structured Content | Foundation | KaTeX parser + AST walker + SVG decomp | LaTeX renders on 95% of test set | Eng | Planned
Q2 | M5-M6 | Structured Content | Foundation | Symbol mapper + fallback glyph registry | Fallback covers 100% of Greek + operators | Eng | Planned
Q2 | M5-M6 | Structured Content | Foundation | Code block handler + Rough.js sketcher | Python/Rust code blocks renderable | Eng | Planned
Q3 | M7-M9 | Realism & Continuation | Realism & Privacy | OCR continuation (Hough + HPP + homography) | Anchor within 2px of physical pen tip | Eng | Planned
Q3 | M7-M9 | Realism & Continuation | Realism & Privacy | Multi-instrument physics (ballpoint/gel/pencil/highlighter) | Turing test < 50% detection | Eng | Planned
Q3 | M8-M9 | Realism & Continuation | Realism & Privacy | WebGL 3D warp + fragment shaders | Coffee-ring overlay visible at 100% zoom | Eng | Planned
Q4 | M10-M12 | Privacy & Safety | Realism & Privacy | Wasm compile (ViT+SAQ+Diffusion INT8) | Bundle < 50 MB; load < 3s on cable | Wasm | Planned
Q4 | M10-M12 | Privacy & Safety | Realism & Privacy | WebGPU acceleration pipeline | 4-7× speedup vs Wasm-only | Wasm | Planned
Q4 | M11-M12 | Privacy & Safety | Realism & Privacy | Steganographic watermark + TS-GATR anomalies | External security audit pass | Security | Planned
Q5 | M13-M15 | Ecosystem | Ecosystem & GTM | Plugin SDK (TS) + VSCode/Obsidian/Notion | 3 plugins in production | DevRel | Planned
Q5 | M13-M15 | Ecosystem | Ecosystem & GTM | MLOps: training pipeline + MLflow registry | CI/CD gate enforces eval threshold | MLOps | Planned
Q5 | M14-M15 | Ecosystem | Ecosystem & GTM | Drift detector + A/B serving | Drift alert within 24h of regression | MLOps | Planned
Q6 | M16-M18 | GTM & A11y | Ecosystem & GTM | Accessibility deep-dive (WCAG 2.2 AA audit) | Deque audit pass | A11y | Planned
Q6 | M16-M18 | GTM & A11y | Ecosystem & GTM | Enterprise SSO + EDU site licensing | 3 EDU pilots signed | Sales | Planned
Q6 | M17-M18 | GTM & A11y | Ecosystem & GTM | GA launch + monetization tiers go live | $10K MRR within 60 days of GA | Sales | Planned

## Hiring Plan
Hiring Plan (18-Month)
Role | Count | Start Quarter | Rationale
Senior full-stack engineer | 2 | Q1 | MVP build
ML research engineer | 2 | Q1, Q3 | Model training + MLOps
Wasm/Rust engineer | 1 | Q2 | Wasm compile + performance
Security engineer | 1 | Q3 | Privacy architecture + threat model
A11y specialist | 1 | Q5 | WCAG audit + dysgraphia research
Designer (UX/brand) | 1 | Q1 | Sandbox UI + visual identity
DevRel | 1 | Q5 | Plugin SDK launch + community
Total | 9 | — | —

## Risk Register
Top-15 Risk Register
# | Risk | Category | Severity | Likelihood | Score | Mitigation | Owner
1 | Signature forgery misuse | Security | 5 | 2 | 10 | Stylus liveness + TS-GATR + legal playbook | Security
2 | Model extraction attack | Security | 4 | 3 | 12 | Rate limit + style-vector watermark | ML
3 | Browser engine fragmentation | Tech | 3 | 4 | 12 | Cross-browser CI matrix + polyfills | QA
4 | WebGPU not available on target devices | Tech | 3 | 3 | 9 | Wasm fallback (3× slower but compatible) | Infra
5 | HTR benchmark drift | Tech | 3 | 3 | 9 | Reference dataset checksums + quarterly re-validation | Eval
6 | Style vector regression after model update | Tech | 4 | 3 | 12 | Drift monitor + auto-rollback | MLOps
7 | GDPR/BIPA enforcement action | Regulatory | 5 | 2 | 10 | Zero-knowledge architecture + DPIA | Legal
8 | Patent infringement (Handwriting Transformers) | Regulatory | 4 | 2 | 8 | Prior-art search + defensive publication | Legal
9 | University RFP cycle misalignment | Market | 3 | 3 | 9 | EDU sales motion starts in Q4 (RFP season) | Sales
10 | Competitor ships similar feature | Market | 3 | 3 | 9 | Ship plugin ecosystem + accessibility moat | Product
11 | Key engineer attrition (single-points-of-failure) | Operational | 4 | 3 | 12 | Documentation + pair programming + retention | Eng
12 | CDN outage (Cloudflare R2) | Operational | 3 | 2 | 6 | Multi-CDN failover (R2 + S3) | Infra
13 | Wasm bundle size regression | Tech | 2 | 3 | 6 | Bundle size budget in CI | Frontend
14 | Plugin SDK API breaking changes | Tech | 3 | 3 | 9 | Semver discipline + deprecation policy | SDK
15 | Accessibility audit fails WCAG 2.2 AA | Regulatory | 4 | 2 | 8 | Quarterly Deque audits + A11y specialist | A11y

## Unit Economics
Pricing Tiers & Unit Economics
Metric | Free | Pro | Teams | EDU Site | Enterprise
Price | $0 | $9/mo | $19/seat/mo | $2/student/yr | Custom
CAC | $8 | $24 | $180 | $400 | $12,000
Annual revenue/user | $0 | $108 | $228 | $2-20 | $10K-100K
COGS/user/yr | $1.20 | $3.50 | $8 | $0.50 | $200
Gross margin | N/A | 97% | 96% | 95% | 98%
LTV (3-yr) | $0 | $280 | $580 | $6-60 | $30K-300K
LTV/CAC | N/A | 11.7x | 3.2x | 15x | 25x
Payback (months) | N/A | 2.7 | 9.5 | 24 | 12